## Sheet1
Name | Date | Task Completed with Details
All Members | 2024-03-18 | Researched about the basics of project on what needs to be done.
Satya | 2024-03-18 | Created the basic structure of the project with necessary details.
All Members | 2024-03-19 | Had a group discussion to create the design of the project and devided the tasks that needed for the project.
Karthik | 2024-03-19 | I downloaded the structure from the one drive posted by Satya and started adding the basics of express app in the js file.
Mani | 2024-03-19 | I downloaded the structure from the one drive posted by Satya and started adding the public folder where the static html files are present.
Ravi | 2024-03-20 | Formed the basic schema required for the login and the car entity.
Satya | 2024-03-20 | Included the static paths for the html file to return it back to the browser using the app.get path.
Ravi | 2024-03-21 | Started working on the FE part for the features of login and registration part.
Mani | 2024-03-21 | Started working on the FE part for the car CRUD operation inputs and displaying fields.
Karthik | 2024-03-22 | Started working on the backend for the api for signin.
Satya | 2024-03-23 | Started working on the backend for the api for login componenet.